## README
S7 · The Launch Readiness Plan — capstone scenario workbook
SAMPLE DATA — TRAINING USE ONLY. Fictional portfolio; safe to upload to Claude.
This is your team’s complete dataset for the Day 3 capstone. Everything you need is in
this one file.
Sheets in this workbook:
• Project Facts — the confirmed [PROPERTY C] fit-out position (from the quarterly report)
• Milestone Schedule — the contractor’s programme, rev 4
• Snag List — open and closed snags by unit and trade
• Fit-out Cost Tracker — committed cost against the contingency allowance
• Occupancy & Income — portfolio context, including the [PROPERTY C] rows
ONE WARNING, WORTH READING TWICE:
This workbook contains exactly ONE planted inconsistency — between its sheets, or
against its own totals. Your verifier’s job is to catch it before it reaches your
briefing. Flag it in your pitch; do not silently pick a side.

## Project Facts
[PROPERTY C] — confirmed project position
Sample data — fictional. Extracted from §5 of the Quarterly Property Operations Report, dated 15 July 2026.
Fact | Detail
Property | [PROPERTY C] — 14-unit tower, fit-out phase
Joinery delivered to site | 2 June 2026
Fit-out duration | Contractor requires six weeks from joinery delivery to practical completion
Cost impact | KWD 18,000 against a KWD 25,000 contingency allowance
Contractor | [CONTRACTOR B] — performance review outstanding
Board position | Revised handover date proposed, not yet ratified
Tenant position | Fit-out crew booked; paying storage costs in the interim

## Milestone Schedule
[PROPERTY C] fit-out milestone schedule (contractor issue, rev 4)
Sample data — fictional. Cross-check actual dates against the Project Facts sheet.
Milestone | Planned | Actual / Forecast | Status | Note
Fit-out contract award | 2026-03-14 | 2026-03-14 | Complete
Joinery order placed | 2026-04-07 | 2026-04-07 | Complete | 3-week quoted lead time
Joinery delivered to site | 2026-04-28 | 2026-05-26 | Complete | Supplier delay
Fit-out works (6 weeks from delivery) | — | in progress | In progress | Contractor requires six weeks from joinery delivery
Practical completion | 2026-06-09 | 2026-07-07 | Forecast | Delivery date + six weeks
Snagging & close-out | — | 2026-07-13 | Forecast | One week allowed
Handover to tenant | 2026-06-16 | 2026-07-14 | Forecast | Subject to Board ratification
Board ratification of revised date | — | pending | Pending | Proposed, not yet ratified
Tenant fit-out start | — | pending | Pending | Tenant crew booked; storage costs running

## Snag List
[PROPERTY C] snag list — as inspected 30 June 2026
Sample data — fictional. Raised during progress inspections; severity per the consultant.
Snag | Unit | Trade | Severity | Status | Description
SN-001 | U-06 | HVAC | Minor | Closed | Diffuser balancing outstanding
SN-002 | U-05 | Joinery | Moderate | Open | Door alignment / trim gaps
SN-003 | U-04 | Finishes | Minor | Open | Paint / tiling touch-ups
SN-004 | U-09 | Fire systems | Minor | Open | Detector head not commissioned
SN-005 | U-14 | Joinery | Moderate | Closed | Door alignment / trim gaps
SN-006 | U-09 | Electrical | Moderate | Closed | Sockets untested or unlabelled
SN-007 | U-02 | HVAC | Minor | Open | Diffuser balancing outstanding
SN-008 | U-09 | HVAC | Moderate | Closed | Diffuser balancing outstanding
SN-009 | U-02 | Electrical | Minor | Open | Sockets untested or unlabelled
SN-010 | U-09 | Fire systems | Moderate | Open | Detector head not commissioned
SN-011 | U-02 | Finishes | Minor | Open | Paint / tiling touch-ups
SN-012 | U-12 | Fire systems | Minor | Open | Detector head not commissioned
SN-013 | U-02 | Joinery | Moderate | Open | Door alignment / trim gaps
SN-014 | U-13 | Joinery | Moderate | Open | Door alignment / trim gaps
SN-015 | U-08 | HVAC | Major | Open | Diffuser balancing outstanding
SN-016 | U-02 | Finishes | Minor | Open | Paint / tiling touch-ups
SN-017 | U-14 | Joinery | Moderate | Open | Door alignment / trim gaps
SN-018 | U-09 | Finishes | Minor | Closed | Paint / tiling touch-ups
SN-019 | U-07 | Plumbing | Major | Closed | Pressure test pending
SN-020 | U-01 | Plumbing | Minor | Closed | Pressure test pending
SN-021 | U-01 | Fire systems | Major | Closed | Detector head not commissioned
SN-022 | U-02 | Plumbing | Minor | Open | Pressure test pending
SN-023 | U-12 | Finishes | Moderate | Closed | Paint / tiling touch-ups
SN-024 | U-14 | Plumbing | Major | Open | Pressure test pending
SN-025 | U-05 | Electrical | Moderate | Closed | Sockets untested or unlabelled
SN-026 | U-06 | Plumbing | Moderate | Open | Pressure test pending
SN-027 | U-13 | Joinery | Moderate | Closed | Door alignment / trim gaps
SN-028 | U-12 | Joinery | Minor | Closed | Door alignment / trim gaps

## Fit-out Cost Tracker
[PROPERTY C] fit-out variation cost tracker
Sample data — fictional. Committed variations against the KWD 25,000 contingency allowance.
Line | Variation | Committed (KWD) | Forecast (KWD) | Note
V-01 | Joinery re-delivery and crane hire | 4200 | 4200 | Supplier delay recovery
V-02 | Extended site preliminaries (3 weeks) | 5400 | 5400 | Contractor time-related costs
V-03 | Out-of-hours working to recover programme | 3600 | 4400 | Forecast rises if slip continues
V-04 | Tenant storage cost contribution | 2800 | 3600 | Accruing weekly until handover
V-05 | Design change — unit U-07 partition | 2000 | 2000 | Approved
| Total committed | 18000 | 19600 | Contingency allowance: KWD 25,000

## Occupancy & Income
Occupancy and income by month
Sample data — fictional portfolio. Jan–Jun 2026. Footfall tracked at the retail asset only.
Month | Property | Type | Units | Units Let | Occupancy % | Monthly Rent (KWD) | Collection % | Footfall
2026-01 | [PROPERTY A] | Retail centre | 48 | 40 | 83.3 | 179640 | 98.1 | 214000
2026-01 | [PROPERTY B] | Mixed-use tower | 62 | 57 | 91.9 | 221388 | 98.4
2026-01 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0
2026-02 | [PROPERTY A] | Retail centre | 48 | 39 | 81.2 | 175149 | 97.8 | 208500
2026-02 | [PROPERTY B] | Mixed-use tower | 62 | 57 | 91.9 | 221388 | 98.2
2026-02 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0
2026-03 | [PROPERTY A] | Retail centre | 48 | 38 | 79.2 | 170658 | 97.4 | 203000
2026-03 | [PROPERTY B] | Mixed-use tower | 62 | 56 | 90.3 | 217504 | 97.9
2026-03 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0
2026-04 | [PROPERTY A] | Retail centre | 48 | 38 | 79.2 | 170658 | 96.9 | 199500
2026-04 | [PROPERTY B] | Mixed-use tower | 62 | 56 | 90.3 | 217504 | 97.6
2026-04 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0
2026-05 | [PROPERTY A] | Retail centre | 48 | 37 | 77.1 | 166167 | 96.5 | 194000
2026-05 | [PROPERTY B] | Mixed-use tower | 62 | 56 | 90.3 | 217504 | 97.1
2026-05 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0
2026-06 | [PROPERTY A] | Retail centre | 48 | 36 | 75 | 161676 | 96.2 | 188500
2026-06 | [PROPERTY B] | Mixed-use tower | 62 | 56 | 90.3 | 217504 | 96.8
2026-06 | [PROPERTY C] | Under construction | 14 | 0 | 0 | 0